## Sheet1
ID | Theme | As a/an | I want to | so that | Notes | Sprint # | Assigned To | Start | Finish | Priority | Difficulty | Status | Story Points | Assigned to Sprint
1 | Functional | Client | search for procedures based on Cost | I can choose the best facility for me |  | 2 | R.C, H.Z | 2020-03-02 | 2020-06-02 | 5 | 2 | Done | 9 | Yes
2 | Functional | Client | select procedures using a search-bar | I can find the procedure I will undertake |  | 1 | A.R | 28/2/2020 | 30/3/2020 | 3 | 2 | Done | 2 | Yes
7 | Functional | Client | see facilities of the procedure on a map | I can see how far away my options are |  | 1 | F.S | 28/1/2020 | 31/1/2020 | 5 | 4 | Done | 2 | Yes
8 | Non-functional | Client | access the search procedures in a clear and accessible manner. | I can easily understand what is being shown |  | 1 & 2 | A.R & C.H | 2020-03-02 | 2020-03-02 | 2 | 3 | Done | 2 | Yes
9 | Functional | Client | sort results by Ratings | I can choose the best facility for me |  | 2 | R.C, H.Z | 2020-03-02 | 2020-06-02 | 3 | 1 | Done | 7 | Yes
10 | Functional | Client | search for procedures based on Ratings | I can choose the best facility for me |  | 2 | R.C, H.Z | 2020-03-02 | 2020-06-02 | 5 | 2 | Done | 1 | Yes
11 | Functional | Client | search for facilities based on Distance | I can choose the best facility for me |  | 1 |  | 27/1/2020 | 30/2/2020 | 5 | 3 | Done | 1 | Yes
12 | Functional | Client | enter my current location. | The website knows how far facilities are from me |  | 1 | C.H | 28/1/2020 | 29/1/2020 | 4 | 3 | Done | 1 | Yes
14 | Functional | Client | sort procedures by cost | I can choose the best facility for me |  | 2 | N.D | 2020-03-02 | 2020-04-02 | 4 | 1 | Done | 2 | Yes
15 | Functional | Client | enter a pre-determined location. | The website knows how far facilities are from me |  | 1 | A.R | 28/1/2020 | 30/1/2020 | 4 | 3 | Done | 1 | Yes
17 | Non-functional | Purchaser | have the database contain data from the CMS medical Data set | the data in the website uses standardised data |  | 1 | R.C | 27/1/2020 | 29/1/2020 | 4 | 2 | Done | 2 | Yes
18 | Functional | Purchaser | have the database contain queries for the different procedure searches. | the website can search the database for results to display |  | 1, 2 | R.C, H.Z | 27/1/2020 | 2020-04-02 | 4 | 3 | Done | 8 | Yes
19 | Non-functional | Purchaser | have the website provide its data via Java | the website can access the data entries in the database |  | 1 | N.D, H.Z | 27/1/2020 | 2020-04-02 | 4 | 3 | Done | 2 | Yes
22 | Functional | Client | Click on a facility name and have it behave like clicking a marker | I can navigate the website easier |  | 2 | C.H | 2020-04-02 | 2020-06-02 | 3 | 3 | Done | 2 | Yes
23 | Functional | Purchaser | have search results dynamically generate based on search conditions | clients can view what they searched for |  | 2 | A.R, N.D | 2020-05-02 | 2020-06-02 | 3 | 2 | Done | 1 | Yes
24 | Functional | Client | leave a Review of a procedure I have had | I can help other clients find the right procedure in the future |  | 2 | -------------------- | ----------- | ------------- | 1 | 2 | To do | 1 | Yes
25 | Functional | Purchaser | have test functions for SQL procedures | I know everything is working I the backend |  | 2 | H.Z, N.D R.C | 2020-03-02 | 2020-06-02 | 4 | 2 | Done | 1 | Yes
26 | Non-functional | Client | see a colour associated with the procedures cost | I can understand the rance of pricing at a glance |  | 2 | F.S | 2020-04-02 | -------------- | 3 | 2 | In Progress | 2 | Yes
27 | Non-functional | Purchaser | use machine learning to assist searches | clients can operate the website easier | Very unlikely to happen | 2 | R.C | 2020-06-02 | 2020-07-02 | 1 | 4 | Done | 2 | Yes
28 | Functional | Purchaser | stop Clients from selecting a minimum cost greater than the maximum cost | they don't have no results being displayed |  | 2 | A.R. | 2020-07-02 | 2020-07-02 | 1 | 3 | Done | 2 | No
29 | Non-Functional | Purchaser | sort procedures by distance | I can choose the best facility for me |  | 2 | N.D | 2020-06-02 | 2020-07-02 | 5 | 3 | Done | 3 | Yes