## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
8
|  |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0
|  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
|  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
|  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 18 | 14
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Sprint 2 Backlog
MEDICAL PROCEDURE MAP SPRINT #2 BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a Client, I want to sort results by Ratings
Impliment Ratings into SQL Database | 1 | R.C | Complete | 1 | 1 | 1
Generation of SQL Method(s) | 1 | R.C | Complete | 2 | 1 | 0
Generation of JavaCode | 1 | R.C | Complete | 1 | 0 | 1
Generation of Testing | 1 | H.Z | Complete | 2 | 1 | 1
Implementation on frontend | 1 | A.R. | Complete | 1 | 0 | 1
The database should contain queries for the different procedure searches.
Generation of SQL Procedures | 2 | R.C | In Progress | 8 | 3 | 4
Generation of JavaCode | 2
Implementation on frontend | 2
Generation of Test Driven | 2 | H.Z
As a Client, I want to sort procedures by cost
Generation of SQL Method(s) | 2 | R.C | Complete | 1 | 1
Generarton of Java Related Code | 2 | R.C/H.Z | Complete | 1 | 1
Implementation on frontend | 2 | A.R. | Complete | 1 |  | 1
Cost is shown in 2dp | 1 | C.H | Complete | 1 |  |  | 0.5
Generation Of testing | 2 | H.Z | In Progress
As a Purchaser, I want the search results to be dynamically generated based on the customer search conditions. |  |  |  | 1
Lowest distance to Highest distance | 1 | N.D. | In Progress | 2 | 5
Highest Cost to Lowest Cost
Highest Rating to Lowest Rating
Task
As a Client, I want to leave a Review of a procedure I have had
Generation of SQL Procedure | 1 | R.C. | Complete | 1 | 1 | 0
Generation of JavaCode
Task
Task
As a Client, I want to access the search procedures in a clear and accessible manner.
CSS animations to help useability | 1 | C.H | Complete | 1 | 2 | 1
Implementing animations in website | 2 | C.H | Complete | 2 | 5 | 4 | 2
Table cell click behaves like marker click | 2 | C.H | In Progress | 2 | 0 | 3 | 2
View cost in table | 1 | C.H | Complete | 1 |  |  | 0.5
Create test functions for search SQL procedures via distance.
SQL procedure does not return an empty table | 1 | N.D. | Complete | 0.5 | 0 | 0.5
SQL procedure does not return rows of different sizes | 1 | N.D. | Complete | 0.5 | 0 | 0.5
SQL procedure does not return any null entries or empty strings | 1 | N.D. | Complete | 0.5 | 0 | 0.5
| 1 | A.R. | In Progress | 0.5 |  | 1
| 1 | A.R. | In Progress | 0.5 |  | 0.5
As a client, I want to see a color associated with the procedure's cost
Implimenting javascript to change cost colour with hard-coded values | 1 | F.S | Complete | 0.5 | 1
Recieving cost of procedure from SQL | 1 | F.S | Complete | 0.5 | 0 | 1
Changing colour of map marker | 1 | F.S | Complete | 1.5 | 0 | 1.5
Task
As a client, I want to see the facilities rating when I click it's marker
Implimenting hard-coded javascript to display star rating | 1 | F.S | Complete | 1 | 1
Refacotring code to use actual values | 1 | F.S | In Progress | 1 | 0 | 2
Task
Task
Create test functions for search SQL procedures via cost.
SQL procedure does not return an empty table | 1 | N.D. | In Progress | 0.5 | 0 | 0.5
SQL procedure does not return rows of different sizes | 1 | N.D. | In Progress | 0.5 | 0 | 0.5
SQL procedure does not return any null entries or empty entries | 1 | N.D. | In Progress | 0.5 | 0 | 0.5
Procedure returns costs between the limits | 1 | A.R. | In Progress | 0.5 |  | 1
Procedure returns reviews above the minimum | 1 | A.R. | In Progress | 0.5 |  | 0.5
Refacotring geocoding to use data from SQL
Recieve lat/long from database | 1 | F.S | Complete | 1 | 0 | 0.5
Replace geocoding address with lat/long | 2 | F.S | Complete | 2 | 0 | 2
Calculating distance between client location and hospital locations
Returning a hospital list with distances associated with each hospital relative to users's location. | 1 | N.D. | Complete | 1 | 0 | 2 | 2
Sort hosptial distance by shortest to longest hospital distance away from user
Returning a hospital list with shortest distances first. | 2 | N.D. | Complete | 1 | 0 | 2 | 2
TOTAL |  |  |  | 43.5 | 23 | 34 | 9 | 0 | 0 | 0
Day 1 Notes:
C.H - I had trouble with the eclipse workspace until late in the day so couldnt test any changes made to the website. worked on documentation in paralell
Day 2 Notes:
C.H - New user stories were considered so I updated the product backlog accordingly
R.C - Updated Methods to reflect more accurate information, Meaning re-evaluation of esitmated time

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.