## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
8
|  |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0
|  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
|  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
|  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 18 | 14
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Sprint 2 Backlog
MEDICAL PROCEDURE MAP SPRINT #2 BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a Client, I want to sort results by Ratings
Impliment Ratings into SQL Database | 1 | R.C | Complete | 1 | 1
Generation of SQL Method(s) | 1 | R.C | Pending Review | 2 | 1
Generation of JavaCode | 1
Generation of Testing | 1 | H.Z
Implementation on frontend | 1
The database should contain queries for the different procedure searches.
Generation of SQL Procedures | 2 | R.C | In Progress | 8 | 3
Generation of JavaCode | 2
Implementation on frontend | 2
Generation of Test Driven | 2 | H.Z
As a Client, I want to sort procedures by cost
Generation of SQL Method(s) | 2 | R.C | Pending Review | 1 | 1
Generarton of Java Related Code | 2
Implementation on frontend | 2
Generation Of testing | 2 | H.Z
As a Purchaser, I want the search results to be dynamically generated based on the customer search conditions. |  |  |  | 1
Lowest distance to Highest distance | 1 | N.D. | In Progress | 2 | 5
Highest Cost to Lowest Cost
Highest Rating to Lowest Rating
Task
As a Client, I want to leave a Review of a procedure I have had
Generation of SQL Procedure | 1 | R.C. | Complete | 1 | 1
Generation of JavaCode
Task
Task
As a Client, I want to access the search procedures in a clear and accessible manner.
CSS animations to help useability | 1 | C.H | In Progress | 1 | 2
Implementing animations in website | 2 | CH | In Progress | 2 | 5
Task
Task
User Story #6
Task
Task
Task
Task
TOTAL |  |  |  | 19 | 19 | 0 | 0 | 0 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.