## Product Backlog
ID | Theme | As a/an | I want to | so that | Notes | Priority | Difficulty | Status
1 | Functional | Client | search for procedures based on Cost | I can choose the best facility for me |  | 5 | 2 | In Production
2 | Functional | Client | select procedures using a search-bar | I can find the procedure I will undertake |  | 3 | 2 | Done
3 | Functional | Client | see the price of my procedure with, or without, health insurance | I can choose the best facility for me | May change according to clients wishes | 1 | 1 | To do
4 | Functional | Client | see a loading screen while the application is loading. | I know the website is still working while loading |  | 1 | 3 | To do
5 | Functional | Client | view a ranking system of all the hospitals | I can choose the best facility for me |  | 1 | 4 | In Production
6 | Functional | Client | see recommendations of the highest ranked hospitals for a procedure | I can choose the best facility for me |  | 1 | 5 | To do
7 | Functional | Client | see facilities of the procedure on a map | I can see how far away my options are |  | 5 | 4 | Pending review
8 | Non-functional | Client | access the search procedures in a clear and accessible manner. | I can easily understand what is being shown |  | 2 | 3 | In Production
9 | Functional | Client | sort results by Ratings | I can choose the best facility for me |  | 3 | 1 | To do
10 | Functional | Client | search for procedures based on Ratings | I can choose the best facility for me |  | 5 | 2 | To do
11 | Functional | Client | search for facilities based on Distance | I can choose the best facility for me |  | 5 | 3 | Pending review
12 | Functional | Client | enter my current location. | The website knows how far facilities are from me |  | 4 | 3 | Done
13 | Functional | Client | sort procedures by Distance of the facility | I can choose the best facility for me |  | 4 | 2 | In Production
14 | Functional | Client | sort procedures by cost | I can choose the best facility for me |  | 4 | 1 | In Production
15 | Functional | Client | enter a pre-determined location. | The website knows how far facilities are from me |  | 4 | 3 | Pending review
16 | Non-functional | Purchaser | have the database updated each year with the newest up to date Dataset | I don’t have to worry about out of date data |  | 1 | 2 | To do
17 | Non-functional | Purchaser | have the database contain data from the CMS medical Data set | the data in the website uses standardised data |  | 4 | 2 | Done
18 | Functional | Purchaser | have the database contain queries for the different procedure searches. | the website can search the database for results to display |  | 4 | 3 | Pending review
19 | Non-functional | Purchaser | have the website provide its data via Java | the website can access the data entries in the database |  | 4 | 3 | Done